## Project Management Plan
Week | Tasks | Difficulty
2024-04-15 | Create Project Planning Documents | Medium
2024-04-22 | Trello Setup | Easy
| Git + Github Setup | Easy
2024-04-29 | Create Project | Medium
| Create Project scaffolding | Easy
2024-05-04 | Run App on local | Medium
| Run App on Azure Bash | Easy
2024-05-11 | Config Github Actions | Medium
| Test Github Actions | Easy
2024-05-18 | Config Azure Devops Organization and Project | Easy
| Connect Azure Devops with Github | Easy
2024-05-25 | Create Azure Pipeline | Hard
| Test Run Azure Pipeline | Medium
2024-06-01 | Config locust test | Medium
| Run locust test | Easy
2024-06-08 | Update Readme file | Easy
| Take Screenshots | Easy
| Record a demo video | Medium
2024-06-15 | Q&A | Medium
| Goals | Goals
Q2 | Complete create and run the project on local
Q3 | Complete project CI/CD on Azure Services
Q&A
Yearly Plan | Enhancement, Maintenance and Expansion of new Modules

## Q2
Week | Tasks | Difficulty
2024-04-15 | Create Project Planning Documents | Medium
2024-04-22 | Trello Setup | Easy
| Git + Github Setup | Easy
2024-04-29 | Create Project | Medium
| Create Project scaffolding | Easy
2024-05-04 | Run App on local | Medium
| Run App on Azure Bash | Easy
2024-05-11 | Config Github Actions | Medium
| Test Github Actions | Easy
| Goals | Goals
Q2 | Complete create and run the project on local

## Q3
Week | CI | Difficulty
2024-05-18 | Config Azure Devops Organization and Project | Easy
| Connect Azure Devops with Github | Easy
2024-05-25 | Create Azure Pipeline | Hard
| Test Run Azure Pipeline | Medium
2024-06-01 | Config locust test | Medium
| Run locust test | Easy
2024-06-08 | Update Readme file | Easy
| Take Screenshots | Easy
| Record a demo video | Medium
2024-06-15 | Q&A | Medium
| Goals | Goals
Q3 | Complete project CI/CD on Azure Services
Q&A